## RollCheck Plan
⚡ RollCheck Attendance — Module Setup
6-Sprint Agile Execution Plan · 50-Day Duration · Project: RollCheck Attendance
Sprint 1 – Architecture, Data Flow & Database Foundation
Epic: RC-ARCH: System Architecture and Core Foundations
# | Module | Tasks / Sub-tasks | Ticket IDs
1 | Navigation & App Bootstrap | · Navigation graph design | RC-ARCH-01
· Route and deep-link mapping
· App entry bootstrap flow
2 | Room Database & Persistence Layer | · Classes & students schema | RC-ARCH-02
· Session attendance table
· Active sessions schema
· Manual recovery baseline table
3 | Repository & Domain Managers | · Repository interface design | RC-ARCH-03
· Manager layer data flow
· Domain event mapping
4 | Preferences & Session State | · DataStore/SharedPrefs setup | RC-ARCH-04
· App boot state machine
· Session-state restoration
Sprint 2 – UI Design and Prototype Development
Epic: RC-UI: Core User Interface and Reusable Components
# | Module | Tasks / Sub-tasks | Ticket IDs
1 | Home & Entry Screens | · Home screen layout | RC-UI-01
· Class list UX
· Empty-state and loading views
2 | Roll Call UI | · Roll call prototype | RC-UI-02
· Student card design
· Swipe / mark interaction
3 | Summary & Result UI | · Summary screen prototype | RC-UI-03
· Result breakdown layout
· Export action surface
4 | Shared UI Components & Theme | · Reusable dialogs & cards | RC-UI-04
· Color tokens & typography
· Dark/light theme system
· Icon set integration
Sprint 3 – Core Feature Implementation
Epic: RC-CORE: Attendance Logic, PIN Security, and Recovery
# | Module | Tasks / Sub-tasks | Ticket IDs
1 | Authentication & Security | · PIN setup flow | RC-CORE-01
· PIN login & validation
· PIN update & delete protection
2 | Session Start & Recovery | · Session start logic | RC-CORE-02
· Session recovery on re-launch
· Back-stack safety guard
3 | Roll Call & TTS | · Attendance mark logic | RC-CORE-03
· TTS name announcement
· Roll call state machine
4 | MPS & Manual Attendance | · MPS flow implementation | RC-CORE-04
· Manual attendance entry
· Conflict resolution logic
5 | Summary & Result Flow | · Finalization logic | RC-CORE-05
· Result computation
· Post-session navigation
Sprint 4 – Excel Integration and Export
Epic: RC-EXCEL: Workbook Validation, Write Safety, and Export
# | Module | Tasks / Sub-tasks | Ticket IDs
1 | Excel Validation & Import | · Template structure validation | RC-EXCEL-01
· Class sheet detection
· Error/warning surface
2 | Student Sync & Edit Workbook | · Student parsing from sheet | RC-EXCEL-02
· Sync to Room DB
· Edit-student workbook write-back
3 | Attendance Excel Write Logic | · Attendance cell mapping | RC-EXCEL-03
· Continuous session columns
· Format preservation on write
4 | PDF & Excel Export | · PDF generation (Apache POI/iText) | RC-EXCEL-04
· Excel export formatting
· File naming convention
5 | Public Folder Access | · SAF / MediaStore integration | RC-EXCEL-05
· Public attendance folder
· Export destination picker
Sprint 5 – Reliability, Error Handling & UI Refinement
Epic: RC-HARDEN: Offline Safety and Product Hardening
# | Module | Tasks / Sub-tasks | Ticket IDs
1 | Reliability & Recovery Hardening | · Switch-app recovery | RC-HARDEN-01
· Kill-app recovery
· State persistence on process death
2 | Validation & Error Messaging | · Large file size warnings | RC-HARDEN-02
· Corrupted file handling
· Edge-case validation messages
3 | Exit & Navigation Safeguards | · Exit popup consistency | RC-HARDEN-03
· Save/discard dialog guard
· Back-navigation polish
4 | UI Polish, Motion, Fonts & Haptics | · Font & scroll refinements | RC-HARDEN-04
· Layout animation pass
· Haptic feedback integration
Sprint 6 – Documentation, Review & Submission
Epic: RC-DOC: Final QA and Delivery Assets
# | Module | Tasks / Sub-tasks | Ticket IDs
1 | QA Documentation | · Module-wise test case prep | RC-DOC-01
· End-to-end test scripts
· Bug tracking template
2 | Delivery Readiness & Review | · Jira work-package closure | RC-DOC-02
· Review checklist completion
· Sprint retrospective notes
3 | Support & Info Assets | · User guide document | RC-DOC-03, RC-DOC-04
· Excel color guide
· Final demo package
· Submission archive
Definition of Done (DoD)
✔ | Compile passes without errors
✔ | Target module flow tested end-to-end
✔ | Room DB and Excel state remain consistent
✔ | Recovery path verified where applicable
✔ | No workbook format regression
✔ | Export and public-folder behavior verified where applicable